## GanttChart
Bodega Central Cadena Minimarket
| Project Start Date | 2025-03-12 |  |  |  | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Sebastian Avello | [5 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28
 | time axis 2025-03-10 to 2025-05-04
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | time axis 2025-03-10 to 2025-05-04
1 | Fase 1: Definición del Proyecto (Semana 1 a 4) |  |  |  | -
0.1 | Plan de trabajo |  |  | 2025-03-12 | 2025-03-14 | 3 | 100%
0.1 | Guia del Estudiante |  |  | 2025-03-13 | 2025-03-18 | 6 | 100%
0.1 | Formativa Fase 1 |  |  | 2025-03-14 | 2025-03-20 | 7 | 100% | bar: 2025-03-17 to 2025-03-23
0.1 | Diario de Reflexión |  |  | 2025-03-15 | 2025-03-20 | 6 | 100%
0.0.1 | Autoevaluación de Competencias |  |  | 2025-03-17 | 2025-03-22 | 6 | 100%
0.0.1 | Autoevaluación |  |  | 2025-03-21 | 2025-03-27 | 7 | 100%
0.1 | Cronograma |  |  | 2025-03-28 | 2025-04-04 | 8 | 100%
0.1 | Presentación Idea Proyecto |  |  | 2025-04-07 | 2025-04-14 | 8 | 100%
1 | Fase 2: Desarrollo del Proyecto (Semana 5 a 15) |  |  |  | -
0.1 | Sprint 1 |  |  | 2025-04-14 | 2025-04-27 | 14 | 100%
0.1 | . Modelado de datos |  |  | 2025-04-14 | 2025-04-20 | 7 | 50%
0.1 | . Arquitectura |  |  | 2025-04-14 | 2025-04-20 | 7 | 25%
0.1 | Levantamiento ambientes |  |  | 2025-04-14 | 2025-04-16 | 3 | 25%
0.1 | Sprint 2 |  |  | 2025-04-28 | 2025-05-11 | 14 | 0%
0.1 | Sprint 3 |  |  | 2025-05-12 | 2025-05-25 | 14 | 0%
0.1 | Sprint 4 |  |  | 2025-05-26 | 2025-06-08 | 14 | 0%
0.1 | Sprint 5 |  |  | 2025-06-09 | 2025-06-22 | 14 | 0%
1 | Fase 3: Presentacion Proyecto (Semana 16 - 18) |  |  |  | -
0.1 | Presentacion a comision |  |  | 2025-06-25 | 2025-06-28 | 4 | 0%
1 | [Task Category] |  |  |  | -
0.1 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 0%
0.1 | [Task] |  |  | 2018-01-30 | 2018-01-30 | 1 | 0%
0.1 | [Task] |  |  | 2018-01-31 | 2018-01-31 | 1 | 0%
0.1 | [Task] |  |  | 2018-02-01 | 2018-02-01 | 1 | 0% | bar: 2025-05-01 to 2025-05-04
0.1 | [Task] |  |  | 2018-02-02 | 2018-02-02 | 1 | 0%
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | -
0.1 | . [ Level 2 Task ] |  |  |  | -
0.0.1 | . . [ Level 3 Task ] |  |  |  | -
0.0.0.1 | . . . [ Level 4 Task ] |  |  |  | -
Note on A7: ====== ID#AAABTHx9yaU Vertex42 (2024-09-06 02:25:36) Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: ====== ID#AAABTHx9yZ8 Vertex42 (2024-09-06 02:25:36) Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: ====== ID#AAABTHx9yaE Vertex42 (2024-09-06 02:25:36) Task Lead Enter the name of the Task Lead in this column.
Note on D7: ====== ID#AAABTHx9yaM Predecessor Tasks (2024-09-06 02:25:36) You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: ====== ID#AAABTHx9yac Vertex42 (2024-09-06 02:25:36) Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: ====== ID#AAABTHx9yaA End Date (2024-09-06 02:25:36) The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: ====== ID#AAABTHx9yaI Vertex42 (2024-09-06 02:25:36) Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: ====== ID#AAABTHx9yaQ Vertex42 (2024-09-06 02:25:36) Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).